## Projected_Annual_Sales
Plant Type | 2026 | 2027 | 2028 | 2029 | 2030
Plant A | 1.5 | 1.1 | 0.8 | 0.5 | 0
Plant B | 0 | 0.1 | 0.3 | 0.5 | 0.6
Plant C | 0.6 | 1.2 | 0.6 | 1.2 | 0.6

## Yield_Per_Shelf
Plant Type | Yield per Shelf (tons/year)
Plant A | 0.5
Plant B | 0.3
Plant C | 0.4

## Personnel_Requirements
Year | Total Production (tons) | Direct Workers | Team Leaders | Technicians
2026 | 2.1 | 21 | 5 | 2
2027 | 2.4 | 24 | 5 | 3
2028 | 1.7 | 17 | 5 | 3
2029 | 2.2 | 22 | 5 | 3
2030 | 1.2 | 11 | 5 | 2

## Sheet1
Activity | Designation | Immediate Predecessors | steps | Duration (weeks)
Research on the growing process of the new plants | A |  | 1 | 20
Specifying the required equipment | B |  | 2 | 10
Purchase equipment | C |  |  | 32
Equipment commissioning | D |  |  | 10
Hire workers | E |  |  | 26
Train workers | F |  |  | 12
Negotiate contracts with suppliers | G |  |  | 12
Material delivery by suppliers | H |  |  | 36
Ramp up | I |  |  | 16